## Slide 1: SPRINT 3 RETROSPECTIVE Team R02
SE2 – SPG Sprint 2

## Slide 2: PROCESS MEASURES Macro statistics
Committed Stories: 8 → Done: 8
Committed Points: 42 → Done: 42
Planned hours: 98h → Spent hours: 100h 50m

## Slide 3: PROCESS MEASURES detailed statistics - 1
Story #0: Technical tasks (10 tasks)
Estimated: 72h30min → Actual: 63h50min
Story #15: (Warehouse manager) Acknowledge delivery
Task #1: FE for acknowledge delivery
Task #2: BE for acknowledge delivery
Story points: 2
Estimated: 1h 30m → Actual: 3h30m
Story #16: (Client) Booking change
Task #1: FE for booking change
Task #2: BE for booking change
Story points: 13
Estimated: 1h → Actual: 2h 30min

## Slide 4: PROCESS MEASURES detailed statistics - 2
Story #21: (Shop Employee) Contact client that didn’t pick up the order
Task #1: FE for missed pick-up
Task #2: BE for missed pick-up
Story points: 5
Estimated: 2h → Actual: 3h45m
Story #22: (Manager) Select farmers by their applications
Task #1: FE for select farmers
Task #2: BE for select farmers
Story points: 5
Estimated: 5h → Actual: 5h 15m

## Slide 5: PROCESS MEASURES detailed statistics - 3
Story #23: (Registered client) Receive a reminder email 1 day before the pickup date
Task #1: FE for Notification
Task #2: BE for Notification
Story points: 8
Estimated: 2h → Actual: 4h
Story #24: (Farmer) See changes of products
Task #1: FE for see changes of products
Task #2: BE for see changes of products
Story points: 5
Estimated: 4h → Actual: 4h

## Slide 6: PROCESS MEASURES detailed statistics - 4
Story #25: (Farmer) See the bookings
Task #1: FE for see bookings
Task #2: BE for see bookings
Story points: 2
Estimated: 2h → Actual: 3h
Story #26: (Registered Delivery person) Confirm delivery and payment
Task #1: FE for confirm home delivery
Task #2: BE for confirm home delivery
Story points: 2
Estimated: 8h → Actual: 11h

## Slide 7: Detailed Statistics
Average Hour per task : 100.8(hours)/ 26(#tasks) = 3.87 hours
Standard deviation: 0.54
Total task estimation error ratio: 0.972

## Slide 8: QUALITY MEASURES UNIT TESTING
Total hours estimated: 30h (30h for implementing tests)
Total hours spent: 13h (13h of testing)
Nr of automated unit test cases: -----modify---- 30 for BE + 42 for FE = 72 unit test cases
Coverage: 0% (Could not get SonarCloud to read the coverage – we estimated it to be around 22% based on the outputs of the testing)

## Slide 9: QUALITY MEASURES E2e testing
Total hours estimated: 8h (1h per story) - included inside each story
Total hours spent: 8h

## Slide 10: QUALITY MEASURES Code review
Total hours estimated: 8h (1h per story) - included inside each story
Total hours spent: 8h

## Slide 11: QUALITY MEASURES Technical debt management
Total hours estimated: 1d 2h 30m
Total hours spent: 1d
Hours estimated for remediation by SonarQube: 3h (only in Maintainability - fixing code smells)
Hours estimated for remediation by SonarQube only for the selected and planned issues: 3h (only in Maintainability - fixing code smells)
Hours spent on remediation: 1d 2h 30m
debt ratio (as reported by SonarQube under "Measures-Maintainability"): 0.3%
rating for each quality characteristic reported in SonarQube under "Measures" (namely reliability, security, maintainability):
  Reliability → A
  Security → A
  Maintainability → A

## Slide 12: Assessment
What caused your errors in estimation (if any)?
Reviewing globally the app and controlling that every story is correctly connected to the others

## Slide 13: Assessment
What lessons did you learn (both positive and negative) in this sprint?
Comment more our code to let the other group mates understand what we did.
Write a general documentation in the readme file (for example write the users credentials).
A good FE needs more development time allocated.

## Slide 14: Assessment
Which improvement goals set in the previous retrospective were you able to achieve?
We have cured more the design of our application and made all the pages responsive
We have added to the read.me file api calls explanations
We have fixed all the past and new issues and the stories left from previous sprint

## Slide 15: Assessment
Which ones you were not able to achieve? Why?
We achieved all of the goals set in the previous retrospective.

## Slide 16: Assessment
Improvement goals for the next sprint and how to achieve them (technical tasks, team coordination, etc.)
We need to increase the technical debt remediation time and to increase the number of technical tasks needed to refactor our code and make the UI responsive.
We plan to develop less stories and focus more on the currently open issues and app visual improvements.

## Slide 17: Assessment
One thing you are proud of as a Team:
We supported each other on any difficulty that appeared.