## Slide 1: SPRINT 3 RETROSPECTIVE Team R02
SE2 – SPG Sprint 3

## Slide 2: PROCESS MEASURES Macro statistics
Committed Stories: 8 → Done: 8
Committed Points: 42 → Done: 42
Planned hours: 98h → Spent hours: 100h 50m

## Slide 3: PROCESS MEASURES detailed statistics - 1
Story #0: Technical tasks (10 tasks)
Estimated: 72h30min → Actual: 63h50min
Story #15: (Warehouse manager) Acknowledge delivery
Task #1: FE for acknowledge delivery
Task #2: BE for acknowledge delivery
Story points: 2
Estimated: 1h 30m → Actual: 3h30m
Story #16: (Client) Booking change
Task #1: FE for booking change
Task #2: BE for booking change
Story points: 13
Estimated: 1h → Actual: 2h 30min

## Slide 4: PROCESS MEASURES detailed statistics - 2
Story #21: (Shop Employee) Contact client that didn’t pick up the order
Task #1: FE for missed pick-up
Task #2: BE for missed pick-up
Story points: 5
Estimated: 2h → Actual: 3h45m
Story #22: (Manager) Select farmers by their applications
Task #1: FE for select farmers
Task #2: BE for select farmers
Story points: 5
Estimated: 5h → Actual: 5h 15m

## Slide 5: PROCESS MEASURES detailed statistics - 3
Story #23: (Registered client) Receive a reminder email 1 day before the pickup date
Task #1: FE for Notification
Task #2: BE for Notification
Story points: 8
Estimated: 2h → Actual: 4h
Story #24: (Farmer) See changes of products
Task #1: FE for see changes of products
Task #2: BE for see changes of products
Story points: 5
Estimated: 4h → Actual: 4h

## Slide 6: PROCESS MEASURES detailed statistics - 4
Story #25: (Farmer) See the bookings
Task #1: FE for see bookings
Task #2: BE for see bookings
Story points: 2
Estimated: 2h → Actual: 3h
Story #26: (Registered Delivery person) Confirm delivery and payment
Task #1: FE for confirm home delivery
Task #2: BE for confirm home delivery
Story points: 2
Estimated: 8h → Actual: 11h

## Slide 7: PROCESS MEASURES detailed statistics - 5
Fixed Git issues in this Sprint:
Navbar color contrast issue  Navbar was completely redesigned
Shopping cart not allowing floating point values  shopping cart now increments the quantity by 0.5 units instead of 1 unit

## Slide 8: Detailed Statistics
Average Hour per task : 100.8(hours)/ 26(#tasks) = 3.87 hours
Standard deviation: 0.54
Total task estimation error ratio: 0.972

## Slide 9: QUALITY MEASURES UNIT TESTING
Total hours estimated: 3d 6h (for implementing tests)
Total hours spent: 1d 5h (of testing)
Nr of automated unit test cases: 46 for BE + 47 for FE = 93 unit test cases
Coverage: 60% (Could not get SonarCloud to read the coverage – we estimated it to be around 60% based on the outputs of the testing)

## Slide 10: QUALITY MEASURES E2e testing
Total hours estimated: 8h (1h per story) - included inside each story
Total hours spent: 8h

## Slide 11: QUALITY MEASURES Code review
Total hours estimated: 8h (1h per story) - included inside each story
Total hours spent: 8h

## Slide 12: QUALITY MEASURES Technical debt management
Total hours estimated: 1d 2h 30m
Total hours spent: 1d
Hours estimated for remediation by SonarQube: 2d (only in Maintainability - fixing code smells)
Hours estimated for remediation by SonarQube only for the selected and planned issues: 1d7h (only in New Code - Maintainability - fixing code smells)
Hours spent on remediation: 1d
Debt ratio (as reported by SonarQube under "Measures-Maintainability"): 0.3%
Rating for each quality characteristic reported in SonarQube under "Measures" (namely reliability, security, maintainability):
  Reliability → A
  Security → A
  Maintainability → A

## Slide 13: Assessment
What caused your errors in estimation (if any)?
Reviewing globally the app and controlling that every story is correctly connected to the others
Making well-designed and responsive pages is not always a straight-forward process

## Slide 14: Assessment
What lessons did you learn (both positive and negative) in this sprint?
Story integration was not as swift as we expected. We faced some initial difficulty on integrating our previously implemented stories with the new ones
Documentation (the Git readme) proved to be very helpful and we often used it as a “manual” to quickly search and get the information we needed
At the end of this sprint we were able to deliver a much better looking and much more responsive app. This step helped us better understand the effects of a better design on the stakeholders feedback and “happiness”

## Slide 15: Assessment
Which improvement goals set in the previous retrospective were you able to achieve?
We have cured more the design of our application and made all the pages responsive
We have added to the readme file all the API calls and the corresponding explanations
We have fixed most of the past and new issues and we have completed all the stories left from previous sprint

## Slide 16: Assessment
Which ones you were not able to achieve? Why?
We achieved all of the goals set in the previous retrospective

## Slide 17: Assessment
Improvement goals for the next sprint and how to achieve them (technical tasks, team coordination, etc.)
We need to further improve the design and the usability of our application
We need to better show the state of our system by showing more meaningful alerts and messages to the user
We plan to increase the amount and granularity of our test suites to achieve a higher coverage and to discover bugs quicker

## Slide 18: Assessment
One thing you are proud of as a Team:
Teamwork, as it was also the case in the previous two sprints, was awesome. We helped each other in solving problems and reviewing code from previously implemented stories