## Slide 1: SPRINT 1 RETROSPECTIVE Team R02
SE2 – SPG Sprint 1

## Slide 2: PROCESS MEASURES Macro statistics
Committed Stories: 8 → Done: 8
Committed Points: 43 → Done: 43
Planned hours: 99h15m → Spent hours: 97h55min

## Slide 3: PROCESS MEASURES detailed statistics - 1
Story #0: Technical tasks (8 tasks)
Estimated: 55h15min → Actual: 50h55min
Story #1: (Shop employee) Enter an order for a client
Task #1: FE for entering client order
Task #2: BE for entering client order
Story points: 8
Estimated: 8h → Actual: 8h
Story #2: (Shop employee) Register new client to the platform
Task #1: FE for registration platform
Task #2: BE for registration platform
Story points: 3
Estimated: 3h → Actual: 45min

## Slide 4: PROCESS MEASURES detailed statistics - 2
Story #3: (Shop employee) Browse the available products
Task #1: FE for browsing available products
Task #2: BE for browsing available products
Story points: 13
Estimated: 12h → Actual: 18h
Story #4: (Shop employee) Handing out products to a client
Task #1: FE for handing out products to a client
Task #2: BE for handing out products to a client
Story points: 5
Estimated: 4h → Actual: 4h

## Slide 5: PROCESS MEASURES detailed statistics - 3
Story #5: (Shop employee) Top-up a client’s wallet
Task #1: FE for topping-up a client’s wallet
Task #2: BE for topping-up a client’s wallet
Story points: 2
Estimated: 4h → Actual: 4h30min
Story #6: (Unregistered user) Register to the platform
Task #1: FE for registration platform
Task #2: BE for registration platform
Story points: 2
Estimated: 3h → Actual: 4h30min

## Slide 6: PROCESS MEASURES detailed statistics - 4
Story #7: (Registered client) Add products to the basket
Task #1: FE for adding products to the basket
Task #2: BE for adding products to the basket
Story points: 8
Estimated: 6h → Actual: 7h
Story #8: (Registered client) Receive a reminder that my wallet balance is insufficient
Task #1: FE for insufficient balance
Task #2: FBE for insufficient balance
Story points: 2
Estimated: 4h → Actual: 3h

## Slide 7: Detailed Statistics
Average Hour per task : 97.9(hours)/ 19(#tasks) = 4.07 hours
Standard deviation: 0.28
Total task estimation error ratio: 1.013

## Slide 8: QUALITY MEASURES UNIT TESTING
Total hours estimated: 30h (6h of studying unit testing methods + 24h for implementing tests)
Total hours spent: 33h (9h of studying unit testing methods + 24h of testing)
Nr of automated unit test cases: 17 for BE + 36 for FE = 53 unit test cases
Coverage: 0%

## Slide 9: QUALITY MEASURES E2e testing
Total hours estimated: 8h (1h per story) - included inside each story
Total hours spent: 6h

## Slide 10: QUALITY MEASURES Code review
Total hours estimated: 8h (1h per story) - included inside each story
Total hours spent: 10h

## Slide 11: QUALITY MEASURES Technical debt management
Total hours estimated: 6h
Total hours spent: 3h
Hours estimated for remediation by SonarQube
Hours estimated for remediation by SonarQube only for the selected and planned issues
Hours spent on remediation
debt ratio (as reported by SonarQube under "Measures-Maintainability"): 0.7%
rating for each quality characteristic reported in SonarQube under "Measures" (namely reliability, security, maintainability):
  Reliability → A
  Security → A
  Maintainability → A

## Slide 12: Assessment
What caused your errors in estimation (if any)?
FE development time was underestimated. We ended up reallocating time from the BE tasks to deliver a good UI for the tasks.
JEST testing proved much more difficult and tricky than we thought
We included also SonarQube analysis under the "Implement test" task, but since the actual JEST testing proved a lot tougher, we ended up not having enough time to properly do the SonarQube analysis.
We forgot to include in the DB task the fact that we needed a certain number of dummy data to be inserted (as requested by the project PDF).

## Slide 13: Assessment
What lessons did you learn (both positive and negative) in this sprint?
Testing, especially the Technical dept part needs more time to be properly done.
The testing and technical debt tasks need to separated.
A good FE needs more development time allocated.

## Slide 14: Assessment
Which improvement goals set in the previous retrospective were you able to achieve?
Tasks were much better divided this time, which in turn decreased e lot the continuous communication efforts needed.

## Slide 15: Assessment
Which ones you were not able to achieve? Why?
We did not succeed in adding the code documentation since by better dividing the tasks, the need for very detailed documentation decreased. This may well prove problematic in the future if we will need to do incremental work on already implemented features.

## Slide 16: Assessment
Improvement goals for the next sprint and how to achieve them (technical tasks, team coordination, etc.)
More time for testing.
By better understanding the current suggestions of Sonarcloud, in the future we can write better code and in turn reduce the remediation efforts.
Testing needs to be treated differently from Technical debt and more time needs to be dedicated to the Technical debt part.

## Slide 17: Assessment
Things we are proud as a team:
Everyone finished all of their tasks and delivered working code.
Team members communication and availability was outstanding.