## Slide 1: SPRINT 2 RETROSPECTIVE Team R02
SE2 – SPG Sprint 2

## Slide 2: PROCESS MEASURES Macro statistics
Committed Stories: 12 → Done: 10
Committed Points: 53 → Done: 15
Planned hours: 99h30m → Spent hours: 102h10m

## Slide 3: PROCESS MEASURES detailed statistics - 1
Story #0: Technical tasks (13 tasks)
Estimated: 53h30min → Actual: 49h30min
Story #9: (Farmer) Declare product availability for next week
Task #1: FE for declaring availability
Task #2: BE for declaring availability
Story points: 8
Estimated: 5h → Actual: 5h30m
Story #10: (Shop employee) Know orders pending cancellation
Task #1: FE for orders pending cancellation
Task #2: BE for orders pending cancellation
Story points: 2
Estimated: 4h30m → Actual: 45min

## Slide 4: PROCESS MEASURES detailed statistics - 2
Story #11: (Registered client) Browse the available products for next week
Task #1: FE for browsing available products for next week
Task #2: BE for browsing available products for next week
Story points: 8
Estimated: 5h → Actual: 3h30m
Story #12: (Registered client) Opt in for home delivery
Task #1: FE for Opt in for home delivery
Task #2: BE for Opt in for home delivery
Story points: 5
Estimated: 5h → Actual: 5h

## Slide 5: PROCESS MEASURES detailed statistics - 3
Story #13: (Registered client) Select pickup date for the purchase
Task #1: FE for selecting pickup date for the purchase
Task #2: BE for selecting pickup date for the purchase
Story points: 2
Estimated: 1h30m → Actual: 1h10min
Story #14: (Farmer) Confirm preparation of booked orders
Task #1: FE for registration platform
Task #2: BE for registration platform
Story points: 2
Estimated: 2h → Actual: 2h30min

## Slide 6: PROCESS MEASURES detailed statistics - 4
Story #17: (Farmer) Confirm bookings for next week
Task #1: FE for confirming bookings for next week
Task #2: BE for confirming bookings for next week
Story points: 2
Estimated: 3h → Actual: 3h
Story #18: (Warehouse worker) Confirm preparation of bags for scheduled pick-up
Task #1: FE for confirming preparation of bags for scheduled pick-up
Task #2: FBE for confirming preparation of bags for scheduled pick-up
Story points: 2
Estimated: 5h → Actual: 7h30m

## Slide 7: PROCESS MEASURES detailed statistics - 5
Story #19: (Registered client) Receive a confirmation of the purchase
Task #1: BE for receiving a confirmation of the purchase
Story points: 2
Estimated: 2h → Actual: 2h
Story #20: (Warehouse manager) Check the pick-up schedule
Task #1: FE for checking the pick-up schedule
Task #2: BE for checking the pick-up schedule
Story points: 5
Estimated: 4h → Actual: 4h

## Slide 8: Detailed Statistics
Average Hour per task : 102.15(hours)/ 36(#tasks) = 2.83 hours
Standard deviation: 0.46
Total task estimation error ratio: 0.97

## Slide 9: QUALITY MEASURES UNIT TESTING
Total hours estimated: 30h (30h for implementing tests)
Total hours spent: 19.5h (19.5h of testing)
Nr of automated unit test cases: 30 for BE + 42 for FE = 72 unit test cases
Coverage: 0% (Could not get SonarCloud to read the coverage – we estimated it to be around 22% based on the outputs of the testing)

## Slide 10: QUALITY MEASURES E2e testing
Total hours estimated: 12h (1h per story) - included inside each story
Total hours spent: 12h

## Slide 11: QUALITY MEASURES Code review
Total hours estimated: 12h (1h per story) - included inside each story
Total hours spent: 12h

## Slide 12: QUALITY MEASURES Technical debt management
Total hours estimated: 9h
Total hours spent: 6h
Hours estimated for remediation by SonarQube: 3h (only in Maintainability - fixing code smells)
Hours estimated for remediation by SonarQube only for the selected and planned issues: 3h (only in Maintainability - fixing code smells)
Hours spent on remediation: 6h
debt ratio (as reported by SonarQube under "Measures-Maintainability"): 0.5%
rating for each quality characteristic reported in SonarQube under "Measures" (namely reliability, security, maintainability):
  Reliability → A
  Security → A
  Maintainability → A

## Slide 13: Assessment
What caused your errors in estimation (if any)?
FE development time was underestimated. We ended up reallocating time from the BE tasks to deliver a good UI for the tasks.
We lost some time in interpreting the meaning of some stories and estimate correctly the time to implement them.
We underestimated the time needed to update the database with the correct tables and columns to support the stories.

## Slide 14: Assessment
What lessons did you learn (both positive and negative) in this sprint?
Comment more our code to let the other group mates understand what we did.
Write a general documentation in the readme file (for example write the users credentials).
A good FE needs more development time allocated.

## Slide 15: Assessment
Which improvement goals set in the previous retrospective were you able to achieve?
We allocated more time for implementing tests.
Remediation effort on new code decreased considerably since we had the chance to learn from SonarCloud how to write better code.
We created an appropriate task for the Technical debt remediation and the result was much better in terms of remediation efforts needed on new code.

## Slide 16: Assessment
Which ones you were not able to achieve? Why?
We achieved all of the goals set in the previous retrospective.

## Slide 17: Assessment
Improvement goals for the next sprint and how to achieve them (technical tasks, team coordination, etc.)
We need to increase the technical debt remediation time and to increase the number of technical tasks needed to refactor our code and make the UI responsive.
We plan to develop less stories and focus more on the currently open issues and app visual improvements.

## Slide 18: Assessment
One thing you are proud of as a Team:
We supported each other on any difficulty that appeared.