## Slide 1: SPRINT 4 RETROSPECTIVE Team R02
SE2 – SPG Sprint 4

## Slide 2: PROCESS MEASURES Macro statistics
Committed Stories: 8 → Done: 6
Committed Points: 81 → Done: 68
Planned hours: 96h 45m → Spent hours: 102h 30m

## Slide 3: PROCESS MEASURES detailed statistics - 1
Story #0: Technical tasks (7 tasks)
Estimated: 59.45h → Actual: 63h 50m
Story #40: (Registered user) Telegram update products available
Task #1: FE for telegram product availability msg
Task #2: BE for telegram product availability msg
Story points: 13
Estimated: 5h → Actual: 5h30m
NOT DONE  Story #41: (Manager) Check unretrieved food
Task #1: FE for checking unretrieved food
Task #2: BE for checking unretrieved food
Story points: 5
Estimated: 5h → Actual: -

## Slide 4: PROCESS MEASURES detailed statistics - 2
Story #42: (Manager) Alert frequent missed pickups
Task #1: FE for missed pick-up alert
Task #2: BE for missed pick-up alert
Story points: 21
Estimated: 1d 1h → Actual: 1d 1h
NOT DONE  Story #43: (Manager ) Client order suspension
Task #1: FE for client suspension
Task #2: BE for client suspension
Story points: 8
Estimated: 3h → Actual: 1d 5h

## Slide 5: PROCESS MEASURES detailed statistics - 3
Story #44: (Registered user) Telegram balance
Task #1: FE for telegram balance notification
Task #2: BE for telegram balance notification
Story points: 13
Estimated: 7h → Actual: 7h
Story #45: (Registered user) Telegram Confirmation
Task #1: FE for telegram confirmation
Task #2: BE for telegram confirmation
Story points: 8
Estimated: 3h → Actual: 3h 30m

## Slide 6: PROCESS MEASURES detailed statistics - 4
Story #46: (Registered user) Telegram reminder
Task #1: FE for telegram reminder
Task #2: BE for telegram reminder
Story points: 8
Estimated: 3h → Actual: 3h 30m
Story #47: (Registered user) Telegram top-up
Task #1: FE for telegram top-up
Task #2: BE for telegram top-up
Story points: 5
Estimated: 2h → Actual: 2h 30m

## Slide 7: PROCESS MEASURES detailed statistics - 5
Fixed Git issues in this Sprint:
Logos on manage orders

## Slide 8: Detailed Statistics
Average Hour per task :102.5(hours)/23(#tasks)= 4.45 hours;
Standard deviation: 0.54
Total task estimation error ratio: 0.956

## Slide 9: QUALITY MEASURES UNIT TESTING
Total hours estimated: 2d 6h (for implementing/integrating tests)
Total hours spent: 1d 3h (of testing)
Nr of automated unit test cases: 46 for BE + 88 for FE = 134 unit test cases
Coverage: around 60% (Could not get SonarCloud to read the coverage – we estimated it to be around 60% based on the outputs of the testing)

## Slide 10: QUALITY MEASURES E2e testing
Total hours estimated: 8h (1h per story - included inside each story) + 6h in design task = 14h
Total hours spent: 6h for stories + 6h for design task = 12h

## Slide 11: QUALITY MEASURES Code review
Total hours estimated: 8h (1h per story) - included inside each story
Total hours spent: 6h

## Slide 12: QUALITY MEASURES Technical debt management
Total hours estimated: 1d 1h 30m
Total hours spent: 6h
Hours estimated for remediation by SonarQube: 4d 3h (only in Maintainability - fixing code smells)
Hours estimated for remediation by SonarQube only for the selected and planned issues: 4d1h (only in New Code - Maintainability - fixing code smells)
Hours spent on remediation: 6h
Debt ratio (as reported by SonarQube under "Measures-Maintainability"): 0.4%
Rating for each quality characteristic reported in SonarQube under "Measures" (namely reliability, security, maintainability):
  Reliability → C (Sonarcloud considers as bugs the usage of some HTML tags like <b>, <i>, <th> etc.)
  Security → A
  Maintainability → A

## Slide 13: Assessment
What caused your errors in estimation (if any)?
Visual design & usability improvement proved really tough (especially making every page design consistent with the rest) so we overspent some hours for this task.
API testing integration proved to be less difficult due to the repetitive nature of the API calls.
The Story #43 (Disabled users) proved very difficult and by sacrificing time for it (still could not finish) we ended up with less time on the Story #41 (Unpicked food) and we completed none of the stories.

## Slide 14: Assessment
What lessons did you learn (both positive and negative) in this sprint?
Since this was the last sprint of the course we were unconsciously influenced by this fact and ended up trying to deliver a “near final” version of our app.
Story integration was not as swift as we expected. We faced difficulty on integrating the Story #43 (Disabled users) with the other stories and this impacted the result of the stories successfully done.
There is no workaround to good design & usability. When upgrading the app design we discovered many usability problems and design inconsistencies.
Sprint presentation should be better prepared according to the Sprint structure.

## Slide 15: Assessment
Which improvement goals set in the previous retrospective were you able to achieve?
Design & usability was very much improved.
Different alerts and interactive buttons were placed throughout the app.
API test suite coverage went up from less than 50% to higher than 80%.

## Slide 16: Assessment
Which ones you were not able to achieve? Why?
We achieved all of the goals set in the previous retrospective

## Slide 17: Assessment
Improvement goals for the next sprint and how to achieve them (technical tasks, team coordination, etc.)
We want to further improve the site design by making it more intuitive, using more icons and creating a very consistent design and work-flow in every page of the app.
We should increase the code documentation for each component that we create. In this way other members can quickly edit and adapt components without breaking the app.
We should try to finish our tasks earlier so there is enough time to check that every new feature is correctly integrated.

## Slide 18: Assessment
One thing you are proud of as a Team:
Cooperation! Every team member did their best to help in delivering a working app for the last sprint of the course.